## APQP
Supplier Advanced Product Quality Planning - Status Report
Supplier： |  |  | Customer：
Location： | Location ： |  | ASDE：
Supplier Code： | Supplier Code ： |  | DV date：
Project leader： | Project leader ： |  | PV date：
Part Number： | Part Number ： |  | SOP Date：
Part No:
Phase 1: Project Planning and definition
NO | 工作项目 | 分类 | PPAP No | 责任人 | 要求 日期 | 递交 日期 | 确认 时间 | 状态 | 批准人 | 参考模板 | 附件 | 备注
1.1 | Received Sourcing Nomination Letter (SNL) | 定点书
1.2 | Quality contract
1.3 | Received Supplier Technical Statement of Work (STSOW) | 规范
1.4 | Design Records of Saleable Product： YANFENG VISTEON Released Engineering Specification / Drawings(1,a) | 规范 | 1,a
1.5 | Drawing list and Drawing change record | 规范 | [7 empty] | 《图纸目录清单》
1.6 | 图纸中是否包含D/TLD特性
1.7 | Supplier Manufacturing Feasibility reviewed and identified（DFM or TQ Review） | 文件
1.8 | Notify supplier of high impact | 文件 | [7 empty] | 《APQP Kick-off Notification Letter》
1.9 | Supplier Team Roster | 文件
1.1 | Program Timing Agreement including APQP item timing plan | Timing
1.11 | Appearance specification alignment | 规范
1.12 | Has the capacity requirement per year been provided? | 产能
1.13 | Early Capacity Verification (CV) self assessment | 产能
Phase 2: Component Design And Development
2.1 | Design FMEA, only if supplier is design responsible | FMEA | 4
2.2 | Design Records of Saleable Product：Special Characteristics list (YANFENG VISTEON Critical VC & YANFENG VISTEON Significant VS) | SCIF | 1,b | [6 empty] | 《特殊特性表单SCIF》
2.3 | D0 D特性存档清单/产品特性质量记录汇总
2.4 | Initial Sub-supplier list | 分供方 | [7 empty] | 《分供方清单》
2.5 | Test list and time plan ( should include sampling plan)alignment with Yanfeng Visteon （试验清单+试验时间计划，实验室）+ 筛选出年度试验清单 | 产品实验
2.6 | Qualified Laboratory Documentation | 产品实验 | 12 | [6 empty] | 《供应商合格实验室文件范例》
2.7 | Identify Manufacturing equipment , facilities action plan for implementation (by pass 要求，定一台备用一台） | 设备
2.8 | Identify tool （eg. Moulding ）action plan for implementation | 模具
2.9 | Identify new testing,measurement equipment and jig action plan for implementation | 测量
2.1 | Records of Tool Design (17.6) | 模具 | 17.6
2.11 | Tool list&Tool Tagging per Visteon and Customer Requirements | 模具 | 17.5 | [6 empty] | 《 模具清单》
2.12 | Safe Launch Plan confirmation if required | 控制计划 | 7,c | [6 empty] | 《Safe Launch Plan》
2.13 | All measurement concept | 测量
Phase3: Process Design And Development
3.1 | PFMEA - in accordance with AIAG manual, current edition(6) | FMEA | 6
3.2 | Process Pre-Launch Flow Chart(5) | 流程图 | 5
3.3 | Pre-Launch Control Plan(7,a) | 控制计划 | 7,a
3.4 | Assembly Production line layout | 产线搭建
3.5 | Measurement System Studies (Gage R&R) (8) | 测量 | 8
3.6 | Evidence of packaging approval (example V1121 file Approval) (17.2) | 包装 | 17.2 | [6 empty] | 《V1121 format 模板》
3.7 | Evidence of IMDS (or equivalent,such asCAMDS) submisison IMDS | IMDS | 17.4 | [6 empty] | 《 IMDS或CAMDS 文件下载说明以及文档范例》
3.8 | Limited sample approval | 样品
Phase4:Component and Process Verfication
4.1 | The lastest version PFMEA (6) | FMEA | 6
4.2 | Mass production Process Flow Chart | 流程图
4.3 | Mass Production Control Plan(7,b) | 控制计划 | 7, b
4.4 | Operator training plan | 培训
4.5 | Assembly Working instruction | 指导书
4.6 | Records of Material/ Performance test results(10) | 产品实验 | 10
4.7 | Dimensional Results(9) | 测量 | 9
4.8 | Initial Process Study(11) | 过程能力 | 11
4.9 | Checking Aids (16) | 测量 | 16 | [6 empty] | 《检查辅具清单》
4.1 | Launch readiness Review | 量产准备 | [7 empty] | 《Visteon Launch Readiness Review》
4.11 | Sample Product Qty (14) | 样品 | 14 | [6 empty] | 《样件图片记录》
4.12 | Master Sample Qty (15) | 样品 | 15 | [6 empty] | 《样件图片记录》
4.13 | Run at Rate data from production trial run (as required by ASDE) (17.1) | 产能 | 17.1 | [6 empty] | 《产能验证&数据确认表Run&Rate》
4.14 | Appearance Approval Report, (AAR) if applicable (per AIAG requirement)(13) | 规范 | 13
4.15 | Final Sub-supplier list(17.3) |  | 17.3
4.16 | Customer Engineering approval, if required(3) | 工程批准 | 3
4.17 | Tool Design and Change Review (17.7) | 模具 | 17.7
4.18 | Approved Engineering Change Documents if applicable(2) | 制程变更 | 2
4.19 | PPAP Task | 文件 | [7 empty] | 《供应商变更申请单SCR》
4.19.1 | PPAP Level | 文件
4.19.2 | PPAP submission reason | 文件
4.19.3 | Approved PSW Cover Page (18) | 文件 | 18 | [6 empty] | 《零件提交保证书PSW》
Phase 5: Validation after start of mass production
5.1 | Safe Launch Plan summary report(7,c) | 控制计划 | 7,c | [6 empty] | 《Safe Launch Plan》
5.2 | Lesson learned | 经验总结
Note on I10: Hong, Xiaodong (X.): program Timing plan alignment
Note on J10: Hong, Xiaodong (X.): supplier submission date
Note on K10: Hong, Xiaodong (X.): ASDE approval date
Note on O10: Hong, Xiaodong (X.): 供应商交付物
Note on C37: Hong, Xiaodong (X.): such as the measurement method ,measurement jigs,measurement place , measurement schedule, number of samples etc.agreed by Yanfeng Visteon :
Note on C57: Hong, Xiaodong (X.): (Supplier needs compplete the LRR self assessment before ASDE onsite Launch Readiness Reviw , The first round LRR can be done 100 days ahead before mass production , The second round LRR can be done 30 days ahead before mass production
Note on C68: Hong, Xiaodong (X.): 初次递交，工程变更，材料变更等;