## 1.时间计划
Supplier Portal -- APQP 时间计划
计划及实际进度
序号 | 任务 | 201701 | 201702 | 201703 | 201704 | 201705 | 201706 | 201707 | 201708 | 201709 | 201710 | 201711 | 201712 | 201801 | 201802 | 201803 | 201804
1 | 启动 Kick off
完成
2 | 方案确定，任务流程，子任务项目细化，报表规划 Plan confirmation,include flow chart,task item,report
跟进中
3 | IT供应商技术方案沟通确定 IT supplier technical review
4 | IT供应商定点 IT supplier sourcing
5 | 软件开发 Software development
6 | 软件测试与验证，流程试运行 sofeware test and validation,tryrun
7 | 软件优化 Software optimize
8 | 供应商培训 Sub-supplier training
9 | 使用新系统 Start to use new system

## 2.主流程
Out side | Level1(Pur) | Level2(ASDE/SQE Superviser) | Level3(ASDE/SQE) | Level4（Supplier） |  |  | Process Number | 内容 | 备注1
[7 empty] | 1 |  | 物料导入方式支持 1.系统接入,对接BPM系统里面的“新产品供应商定点批准单”SNL,用于新项目的所有开模件任务启动 2.系统接入,“工程更改请求单”ECR,确定供应商是否需要重新递交PPAP； 2.Excel导入，适用于电子料PPAP任务批量导入，一般为DV后。 3.手动录入，料号支持手动增加删减， 支持手动料号更改
[7 empty] | 2 | 生成ID 料号+尾缀 ID/料号/品名/ 厂商/窗口信息/ | 1.建立基本信息，包含料号，零件描述，项目名称，项目code，供应商名称，供应商code,任务创建人，责任人，生成任务号码，YFVE DV,PV,SOP时间点 2.建立初始项目人员名单（后续供应商和延锋人员也可添加人员，只有责任人有权限删除无关人员）； 基本信息维护 | 料号+尾缀/品名 厂商信息，厂商号码及相关基本信息
项目初始物料清单和变更的与新增 | [9 empty] | 增加和删减的需求，手动
料号支持手动更改
[7 empty] | 3 |  | 1.任务创建人可以指定责任人； 2.
是否需要给供应商拒收不合理文件和要求的反馈权限？
通知
[7 empty] | 4 |  | 1.传递邮件通知 2.界面新任务提醒； 3.责任人有权限更新项目信息； 4.责任人可接受任务或者退回到上一层
[7 empty] | 5 | 1.生产/非生产物料 2.HIS yes/no 评估附件 | 1.非生产性物料的选项要有，标签一类的产品要直接过掉 2.HIS判定，DFM会议中定义HIS供应商，然后导入到系统里面。 Yes/No 及附件证明
[8 empty] | 1.上传/发送 2.接受/图纸性质 （首次/更新/更新原因） 3.拒绝/拒绝原因 4.确认 | 传递邮件通知 界面新任务提醒 厂商确定图纸更新原因 纠错/规格更改/工程变化 料号是否升级等
更新原因：升级，工艺变化，规格变化，料号是否升级或者纠错(图纸发错，或标注错)
[7 empty] | 6 | 选择参考的结果 （HIS与否 图纸履历(更新时间/料号/发放性质) 任务定义 三大任务模块 各模块具体任务 选择框(开启/关闭) 界面逻辑复杂 | 默认全部模块 支持每个模块默认项目 支持APQP/PPAP/PPQP 递交性质（首次还是变更) 支持PPAP默认level 任务 支持 支持手动修改任务 支持任务人员手动更改（改为内部或其他) 已开启过的任务，如已有文件上传或批准，则前状态变为非有效状态/存档 参见sheet ”5 APQP任务细化" SQE委派任务给供应商；供应商可以自己建立自己的团队，数量是否控制
任务性质：文件传递给厂商/文件上交与YFVE批准/文件上传不需批准
[6 empty] | 接受：图纸获取性质 |  |  |  | 三大主任务 APQP/PPAP/PPQP
默认全部
| 1，如变更是纠错等原因，任务无需重新开启 | [8 empty] | 支持每个模块默认项目 支持APQP和PPAP 递交性质（首次还是变更) 支持PPAP默认level 任务 支持手动修改任务
| 2，如涉及到工艺，料号，工程变动根据需要SQE重新开启必要任务 | [8 empty] | 支持任务人员手动更改（改为内部或其他)
[7 empty] | 7 | 跟踪状态 | 1.任务提醒功能，系统自动提前7天，3天， 1天； 2.超期为红色； 3.未被批准和拒绝的文件厂商可以自动更新，替换无批准状态的文件（未被审批文件只能替换，不能叠加) 4.已批准任务，更新功能锁死，无法更新 5.被拒收任务，锁死旧任务记录和附件，任务重新开启) 参见sheet 3“ 主任务流程细化”
拒绝，保存任务履历,任务不关闭 能够提交SQE拒收履历，用于供应商绩效考核
[7 empty] | 9 |  | 1.自动生成PPAP文件
10
11
3.是否需要分配任务
工程初始信息/包含定点
4.责任人接收料件任务
5. HIS与否
(系统评估结果和附件)
10.各项任务完成完任务关闭
物料批准/项目状态 报表及报告
1.1新产品供应商定点批准单
SNL
6.根据外部输入
任务选择
开启/关闭或重新开启模块及具体任务（APQP/PPQP/PPAP)
图纸发放/及更新
更新图纸/料号
更新信息发放
获取新图纸
非工程变更需求的更新（如细节错误/发放错误)
2. 建立料号，录入基本信息，项目责任人定义
1.4单个料号建立任务
1.3Excel 批量导入
1.2工程更改请求单ECR
YES
7.定期跟踪APQP状态
8.根据外部输入
任务选择
开启/关闭或重新开启模块及具体任务（PPAP/PPQP)
9.ASDE/SQE 上传PSW
11. 项目交接
接受：图纸获取性质
拒绝/原因
确认动作

## 3.主流程任务细化
SQE根据外部输入
开启
关闭
开启 | 系统记录履历，并返回重新递交
系统记录履历，并关闭
根据图纸和变更状态确定是否需要再次开启 如必要纠错，也可再次开启
具体任务清单
任务1
任务2
任务3
任务4
任务5
任务20
选择任务(开启/关闭)
任务3
备注(内容描述)
附件上传
发放
更新(批准前适用)
界面内容
ASDE审批
拒绝
备注
任务递交
关闭
批准
界面内容
开启
界面内容
timing
timing

## 4.PPQP task
V
V
V
V
V
Yes提供证明及信息/No close
Yes提供证明及信息/No close
制样S1
送样至工程
样件图片/授权/目的
相关测量/试验报告
工程确认
工程反馈
问题清单
整改计划
审批结果批准/拒收
批准
未批准
是否有Alert支持
批准证明/样品/报告/有效期
Alert 有效期/数量
根据批准有效期和数量放行
根据Alert有效期和数量放行
拒收
是否有出货需求
有出货需求
无出货需求
出货检验报告
库存处理结果/报废/出货/
S2送样
增加Sn送样任务
样件图片/授权/目的
相关测量/试验报告/分供方
问题清单
整改计划
批准证明/样品/报告/有效期
Alert 有效期/数量
出货检验报告
库存处理结果/报废/出货/数量

## 5.APQP 任务细化
Supplier Advanced Product Quality Planning - Status Report
Supplier： | [5 empty] | Customer：
Location： | Location ： |  |  |  |  | ASDE：
Supplier Code： | Supplier Code ： |  |  |  |  | DV date：
Project leader： | Project leader ： |  |  |  |  | PV date：
Part Name： | Part Number ： |  |  |  |  | SOP Date：
Part No:
Phase 1: Project Planning and definition
NO | 工作项目 | 相关部门 | 是否有系统支持 |  | 分类 | PPAP No | 责任人 | 要求 日期 | 递交 日期 | 确认 时间 | 状态 | 批准人 | 参考模板 | 附件 | 备注
| 任务输入 |  | BPM
1.1 | Received Sourcing Nomination Letter (SNL) | Buyer |  |  | 定点书
1.2 | Received Supplier Statement of Work (SSOW) | Buyer | EP |  | 规范
1.3 | Design Records of Saleable Product： YANFENG VISTEON Released Engineering Specification / Drawings(1,a) | Buyer/PD | EP |  | 规范 | 1,a | [6 empty] | 《图纸目录清单》
1.4 | Drawing list and Drawing change record | Buyer/PD | EP |  | 规范
1.4 | Supplier Manufacturing Feasibility reviewed and identified（DFM or TQ Review） | Buyer/PD |  |  | 文件
1.5 | Notify supplier of high impact | ASDE |  |  | 文件 | [7 empty] | 《APQP Kick-off Notification Letter》
1.6 | Supplier Team Roster | ASDE |  |  | 文件
1.7 | Program Timing Agreement including APQP item timing plan | ASDE/PM/Buyer |  |  | Timing
1.8 | Appearance specification alignment | ASDE/QE/PD |  |  | 规范
1.9 | Has the capacity requirement per year been provided? | Buyer |  |  | 产能
1.1 | Early Capacity Verification (CV) self assessment | ASDE/Buyer |  |  | 产能
Phase 2: Component Design And Development
2.1 | Design FMEA, only if supplier is design responsible(4) | ASDE |  |  | FMEA | 4
2.2 | Design Records of Saleable Product：Special Characteristics list (YANFENG VISTEON Critical VC & YANFENG VISTEON Significant VS)(1,b) | ASDE/PM/PD/ME/QE |  |  | SCIF | 1,b | [6 empty] | 《特殊特性表单SCIF》
2.3 | Sub-supplier list(17.3) | ASDE |  |  | 分供方 | 17.3 | [6 empty] | 《分供方清单》
2.4 | Test plan alignment with Yanfeng Visteon | ASDE/PD/Buyer |  |  | 产品实验
2.5 | Qualified Laboratory Documentation(12) | ASDE |  |  | 产品实验 | 12 | [6 empty] | 《供应商合格实验室文件范例》
2.6 | Identify Manufacturing equipment , facilities action plan for implementation | ASDE/Buyer/PD/PM |  |  | 设备
2.7 | Identify tool （eg. Moulding ）action plan for implementation | ASDE/Buyer/PD/PM |  |  | 模具
2.8 | Identify new testing,measurement equipment and jig action plan for implementation | ASDE/Buyer/PD |  |  | 测量
2.9 | Records of Tool Design (17.6) | ASDE/PD |  |  | 模具 | 17.6
2.1 | Tool list&Tool Tagging per Visteon and Customer Requirements(17.5) | ASDE |  |  | 模具 | 17.5 | [6 empty] | 《 模具清单》
2.11 | Safe Launch Plan confirmation if required(7,c) | ASDE/PD |  |  | 控制计划 | 7,c | [6 empty] | 《Safe Launch Plan》
2.12 | All measurement concept | ASDE/PD |  |  | 测量
2.13 | Pre-production Part Quality Process task (PPQP task) | ASDE/PD |  |  | 样件
2.13.1 | Sample build and delivery plan |  |  |  | Timing
2.13.2 | Supplier quality warrant |  |  |  | 样件 | [7 empty] | 《样件质量保证书 》
2.13.3 | Corrective action plan |  |  |  | 样件 | [7 empty] | 《样件整改计划》
2.13.4 | Material review report |  |  |  | 样件 | [7 empty] | 《材料核审报告》
2.13.5 | Dimension inspection report |  |  |  | 样件 | [7 empty] | 《尺寸检验报告》
2.13.6 | Material and subcontractor list |  |  |  | 样件 | [7 empty] | 《材料及分供方清单》
Phase3: Process Design And Development
3.1 | PFMEA - in accordance with AIAG manual, current edition(6) | ASDE |  |  | FMEA | 6
3.2 | Process Pre-Launch Flow Chart(5) | ASDE |  |  | 流程图 | 5
3.3 | Pre-Launch Control Plan(7,a) | ASDE |  |  | 控制计划 | 7,a
3.4 | Assembly Production line layout | ASDE |  |  | 产线搭建
3.5 | Measurement System Studies (Gage R&R) (8) | ASDE |  |  | 测量 | 8
3.6 | Evidence of packaging approval (example V1121 file Approval) (17.2) | Package Engineer | No plan |  | 包装 | 17.2 | [6 empty] | 《V1121 format 模板》
3.7 | Evidence of IMDS (or equivalent) submisison IMDS(17.4) | ASDE/PM | IMDS/CAMDS |  | IMDS | 17.4 | [6 empty] | 《 IMDS或CAMDS 文件下载说明以及文档范例》
3.8 | Limited sample approval | ASDE/QE/PD |  |  | 样品
Phase4:Component and Process Verfication
4.1 | The lastest version PFMEA (6) | ASDE |  |  | FMEA | 6
4.2 | Mass production Process Flow Chart | ASDE |  |  | 流程图
4.3 | Mass Production Control Plan(7,b) | ASDE |  |  | 控制计划 | 7, b
4.4 | Operator training plan | ASDE |  |  | 培训
4.5 | Assembly Working instruction | ASDE |  |  | 指导书
4.6 | Records of Material/ Performance test results(10) | ASDE/PD |  |  | 产品实验 | 10
4.7 | Dimensional Results(9) | ASDE/PD |  |  | 测量 | 9
4.8 | Initial Process Study(11) | ASDE |  |  | 过程能力 | 11
4.9 | Checking Aids (16) | ASDE/PD |  |  | 测量 | 16 | [6 empty] | 《检查辅具清单》
4.1 | Launch readiness Review | ASDE |  |  | 量产准备 | [7 empty] | 《Visteon Launch Readiness Review》
4.11 | Sample Product Qty (14) | ASDE |  |  | 样品 | 14 | [6 empty] | 《样件图片记录》
4.12 | Master Sample Qty (15) | ASDE/PD | EP |  | 样品 | 15 | [6 empty] | 《样件图片记录》
4.13 | Run at Rate data from production trial run (as required by ASDE) (17.1) | ASDE |  |  | 产能 | 17.1 | [6 empty] | 《产能验证&数据确认表Run&Rate》
4.14 | Appearance Approval Report, (AAR) if applicable (per AIAG requirement)(13) | ASDE/PD |  |  | 规范 | 13
4.14 | Customer Engineering approval, if required(3)(ESER) | PD/Buyer | EP | BPM/PO | 工程批准 | 3
4.15 | Tool Design and Change Review (17.7) | ASDE/PD |  |  | 模具 | 17.7
4.16 | Approved Engineering Change Documents if applicable(2) | ASDE/PD/PM/Buyer/ME | BPM |  | 制程变更 | 2
4.17 | PPAP Task | ASDE |  |  | 文件 | [7 empty] | 《供应商变更申请单SCR》
4.17.1 | PPAP Level | ASDE |  |  | 文件
4.17.2 | PPAP submission reason | ASDE |  |  | 文件
4.17.3 | Approved PSW Cover Page (18) | ASDE |  |  | 文件 | 18 | [6 empty] | 《零件提交保证书PSW》
Phase 5: Validation after start of mass production
5.1 | Safe Launch Plan summary report(7,c) | ASDE |  |  | 控制计划 | 7,c | [6 empty] | 《Safe Launch Plan》
5.2 | Lesson learned | ASED/PD/PM/Buyer |  |  | 经验总结
Note on L10: 作者: program Timing plan alignment
Note on M10: 作者: supplier submission date
Note on N10: 作者: ASDE approval date
Note on R10: 作者: 供应商交付物
Note on E11: 作者: 系统对接，是否支持多个料号？ BPM 系统建立一个ASDE表单
Note on F14: 作者: 项目采购，还是供应商上传？
Note on C35: 作者: such as the measurement method ,measurement jigs,measurement place , measurement schedule, number of samples etc.agreed by Yanfeng Visteon :
Note on C62: 作者: (Supplier needs compplete the LRR self assessment before ASDE onsite Launch Readiness Reviw , The first round LRR can be done 100 days ahead before mass production , The second round LRR can be done 30 days ahead before mass production
Note on C72: 作者: 初次递交，工程变更，材料变更等;

## 6.PPAP任务细化
NO | Task item | Submission Requiement | 要求日期 | 是否需要提交 | 不要提交原因 | 状态 未提交 审核通过 审核未通过 | 参考模板 | 操作 递交 批准 | 递交时间 | 完成日期
1 | Design Records of Saleable Product产品设计记录
| 1.a;YANFENG VISTEON Released Engineering Specification / Drawings延锋伟世通释放的工程规范/图纸 | 1.the latest drawing released by YFVE提供YFVE最新版本的图纸;
2.Need to provide all the drawings whether it is assembly part or sigle part ； 组合件或非组合件均需要提供图纸清单；
3.PCB design record includes the technical document ，profile drawing and DFM/TQ material etc. PCB 设计记录需要包括技术文件，外形图纸，DFM/TQ资料等;
4.LCD design record includes the drawing ，appearance specification or other specification approved by YFVE ；显示屏LCD设计记录包括图纸，外观标准等信息的文件资料以及经过YFVE 批准的规格书签字扫描文档;
| 1.b;Special Characteristics list (YANFENG VISTEON Critical VC & YANFENG VISTEON Significant VS)特殊特性清单(延锋伟世通指定的关键特性&重要特性) | SCIF document should be approved by YFVE SCIF 文件需要经过YFVE 批准
2 | Approved Engineering Change Documents if applicable工程更改批准文件--如果适用
SCR approved by all customer functions as specified on SCR forms供应商变更申请流程规定的所有延锋伟世通成员对SCR的批准文件
3 | Customer Engineering approval, if required顾客工程批准--如果适用
| 3.a;Product Engineering Approval (ESER)产品工程批准(工程样品批准报告) | Supplier need to provide the deviation report if have 如果有偏差认可报告需要一并提交；
3.b;Engineering Test Results (ES, Electronic Component) 工程测试结果(工程规范，电子零部件)
4 | Design FMEA, only if supplier is design responsible设计FMEA，如供应商承担设计
5 | Process Flow Diagrams 过程流程图
Detailed Flow Diagram to YANFENG VISTEON's dock including the inspect,rework,repair and package；包含所有出货至延锋伟世通前的详细过程流程图包括检验，返工，维修，包装;
Special Characteristics confirmed in the SCIF (VC, VS, VM & PTC) must be addressed in the Process Flow Diagram所有在SCIF文件中确认的VC,VS,VM&PTC均须编入过程流程图中
6 | Process FMEA - in accordance with AIAG manual, current edition过程FMEA--依据AIAG手册现行版本
Including Shipping, Handling, Warehousing, Packaging, and Labelling (including Bar Coding labelling),Special Characteristics confirmed in the SCIF (VC, VS, VM & PTC) must be addressed in the Process FMEA涵盖运输，拿持，仓库，包装，标签(含标签条码)，SCIF中确认的VC&VS&VM&PTC须编入PFMEA。
7 | Control Plan控制计划
7.a; Pre-Launch (component PV test plan)预生产(零件生产验证试验计划)
| 7.b; Production (production process controls & in process test plans)正式生产(生产过程控制&在线测试计划) | Special Characteristics confirmed in the SCIF (VC, VS, VM & PTC) must be addressed in the Control PlanSCIF中确认的VC,VS,VM&PTC须编制在控制计划中
Including Shipping, Handling, Warehousing, Packaging, and Labelling (including Bar Coding labelling),Special Characteristics confirmed in the SCIF (VC, VS, VM & PTC) must be addressed in the Control plan 涵盖运输，拿持，仓库，包装，标签(含标签条码)，SCIF中确认的VC&VS&VM&PTC须编入控制计划。
7.c; Safe Launch Plans 安全投产计划
8 | Measurement System Studies (Gage R&R)测量系统分析(量具重复性&再现性)
Gage R&R < 10% &ndc>5 ;Address all 10%< R&R <30% & ndc>5(AIAG MSA Manual, current edition) 量具重复性&再现性<10%. 应说明10%<重复性&再现性<30%的情况(按AIAG当前版测量系统分析手册)
Gage R&R may be performed on Total Variation (TV) or Tolerance band as appropriate 量具重复性&再现性可能是针对总变差和公差带进行
SC 项和新的量具，测量
9 | Dimensional Results尺寸结果
1.Tabular Summary Format (according to AIAG manual) - with 100 % in tolerance results按照AIAG手册汇总格式提交-100%在公差范围内的结果
2.Drawing numbered to correlate with submitted dimensional results and drawing notes提交的测量结果含对应的图纸号及图纸的备注项
3.Note: Data cannot be older than one year注:尺寸测量数据不能超过一年 Note: Any surrogate data must be approved by YANFENG VISTEON's Supplier Performance office 注:所有替代的数据必须被延锋伟世通SQE批准 Note: Number of layouts may be modified with approval from YANFENG VISTEON. Attach approval if applicable注: 延锋伟世通可能调整测量的产品数量, 须附上批准证据
10 | Records of Material/ Performance test results材料/性能试验结果的记录
1.Data should be collected from Production Trial Run parts (per AIAG APQP/Control Plan Manual, current edition) 按照现行的AIAG中APQP/控制计划手册要求，数据须从试生产中收集
2.Any material certification cannot be older than one year (per AIAG PPAP manual, current edition)按照现行的AIAG PPAP手册要求，任何材料认证报告不能超过1年
3.Any surrogate data must be approved by YANFENG VISTEON's Product Engineering office 任何替代数据须得到延锋伟世通产品设计部的批准
4.Test Results need to include:测试结果应包括: - Copy of the specifications called out on the drawing'图纸上的材料规范 - Material Certification with test results (use tabular format from AIAG PPAP manual, current edition)附有试验结果的材料证明(按照现行版本的AIAG手册要求的表格格式) - Approved PV test results by YANFENG VISTEON's Product Engineering office as required"延锋伟世通设计部门批准的PV测试结果
11 | Initial Process Study 初始过程研究
1. At least 100 parts measured and at least 25 subgroups to be considered至少取得100个零件/25个子组的测量结果
2.For each SC/VS and CC/VC. Raw data to be included in the PPAP package.针对每一个SC/VC及CC/VC特性，原始测量数据须在PPAP中提交
3.For all SC/VS's and CC/VC's, if any 1.33 ≤ Ppk/Cpk < 1.67, work plan required 针对每一个SC/VC及CC/VC特性， if any 1.33 ≤ Ppk/Cpk < 1.67须提交改进计划
4.For all SC/VS's and CC/VC's, if any Ppk/Cpk < 1.33, work plan and 100% in process inspection to beimplemented as a control method in the Control Plan (per AIAG PPAP manual, current edition) 针对每一个SC/VC及CC/VC特性，如果 Ppk/Cpk < 1.33，须提交改进计划及执行过程全检并编入控制计划
5.YANFENG VISTEON Supplier Process Characteristic Analysis延锋伟世通供应商过程特性分析要求 5.1 When reporting Pp and Ppk, calculate/estimate Sigma as:提交Pp和Ppk的计算/评价标准差采用 5.2 When reporting Cp and Cpk, calculate/estimate Sigma based on the control charts used: 提交Cp和Cpk，计算/评价标准差基于控制图 I. For Xbar-R charting, s = Rbar/d2 II. For I-MR charting, s = MRbar/1.128 5.3 Ppk, Pp - need to be reported for initial PPAP submissions or for new processes Ppk，Pp-须针对新制程在首次PPAP中提交 5.4 Cpk, Cp - need to be reported on established processes. These processes MUST be stable/in controlCpk, Cp -针对已有的制程提交，该制程须稳定可控
6.The matrix of raw data needs to specify the cavity as appropriate if cavities are considered如须考虑穴号，原始数据矩阵须注明
7.The statistical Capability study must show statistical charts (per AIAG PPAP and SPC requirements)统计过程能力研究须提供统计图(按AIAG PPAP及SPC要求)
8.If the study is being done per cavity, at least 100 parts/cavity and at least 25 subgroups should be considered for each SC and CC. If less than 30 parts/cavity contact SPE/ASPE responsible如果过程能力按穴号进行，针对SC/CC至少提交每穴100件/25组数据，如果每穴少于30件数据，须联络SPE/ASDE
9.Number of parts may be modified with approval from YANFENG VISTEON. Attach approval if applicable部件数量修改须得到延锋伟世通批准，并附上批准证据。
12 | Qualified Laboratory Documentation具有资格实验室的文件要求
ISO 17025 Certification or National Equivalent and Laboratory Scope for supplier providing resultsISO 17025 认证或具相当于国家等级的实验室检测方提供的测量结果
13 | Appearance Approval Report, (AAR) if applicable (per AIAG requirement)外观批准报告，按AIAG要求使用的部件
14 | Sample product 生产件样品
Supplier should sign off the product samples for reference which are retained at the manufacturing site供应商内部签核样品并保留在生产现场生产时参照
15 | Master Samples (ESER sample signed off by YFVE PD ）
ESER sample signed by YFVE PD 延锋伟世通PD签核的ESER样品
16 | Checking Aids ( e.g. documentation of checking fixtures, mounting box, etc.)检查辅具(如检查夹具文件, 安装盒等)
17 | Records of Compliance with Customer-Specific Requirements符合顾客的具体要求的记录
17.1 | Run at Rate data from production trial run (as required by SPE) (N/A for semi conductors)试生产阶段生产节拍数据(如SQE要求)(半导体类不适用)
CV (Capacity Verification) preliminary calculation - calculation sheet available in YANFENG VISTEON Supplier Portal 产能初期计算--计算表单从延锋伟世通窗口获取
17.2 | Evidence of packaging approval (example PICS Approval).
包装批准文件(如V1121)
17.3 | Suppliers list 分供方清单
17.4 | Evidence of IMDS (or equivalent) submisison IMDS提交(或同等提交)记录
Proof of IMDS acceptance IMDS批准证据
17.5 | Tool list模具清单
Comment: All tooling must be tagged in line with YANFENG VISTEON or customer specified requirements.注：所有的模具标记应符合延锋伟世通或客户特定要求.
17.6 | Records of Tool Design模具设计记录
Comment: Tool design drawing need to be part of the PPAP package if YANFENG VISTEON or Customer funded tooling注:属延锋伟世通或客户资产的模具，设计图纸需要作为PPAP文件包的一部分。
17.7 | Tool Design and Change Review模具设计和更改复审
Tool design and tooling changes need to be reviewed where any supplier or sub-supplier tooling has been modified or re-furbished. This should include a review of tool construction versus physical condition of the tool signed off by the supplier.任何供应商或分供方模具修改或重新磨光，模具设计和更改需要复审，包含已被批准的模具结构和实物状态.
18 | Part Submission Warrant (PSW)零件提交保证书(PSW)
19 | approved PSW by SQE ,SQE 批准的PSW 文件; | 1.Copy of the YANFENG VISTEON PSW Warrant 延锋伟世通PSW副本
2. The part weight on the PSW must be entered to four decimal places (i.e., x.xxxx) and be the average weight resulting from measurements of 10 parts.注:PSW填写的部件重量须包含四位小数，测量10个产品，取均值.

## 特殊逻辑(更新与变更)
Out side |  | Level1(Pur) | Level2(ASDE/SQE Superviser) | Level3(ASDE/SQE) | Level4（Supplier）
项目初始物料清单和变更的与新增
是否需要给供应商拒收不合理文件和要求的反馈权限？
非生产性物料的选项要有，标签一类的产品要直接过掉
任务性质：文件传递给厂商/文件上交与YFVE批准/文件上传不需批准
是否需要给供应商拒收不合理文件和要求的反馈权限？
1.未被批准和拒绝的文件厂商可以自动更新，替换无批准状态的文件（未被审批文件只能替换，不能叠加)
2.已批准任务，更新功能锁死，无法更新
3.被拒收任务，锁死旧任务记录和附件，任务重新开启)
拒绝，保存任务履历，并重新开启
启动项目/建立项目
分配任务到SQE
建立/增加/删减物料清单
（定点后，包含厂商信息，及窗口)
SSOW/图纸上传
分配任务到SQE Superviser
BOM/ECR
获取图纸及工程信息/包含定点
接收料件任务
HIS与否
(系统内嵌评估表)
接收信息及任务
其他输入厂商信息
(SCIF?ESER设计其他相关信息)
发送任务完成通知与
ASDE审批
关闭
反馈问题
(批准/拒绝)
重大异常和风险/代替issue list
物料批准/项目状态 报表及报告
项目kick off
工程输入
根据外部输入
任务选择
开启/关闭或重新开启
分配任务/启动任务流
（APQP/PPAP/PPQP）
ECR/及图纸要求更新
更新图纸/料号
更新信息发放
获取新图纸
具体任务开启/通知
任务反馈证据内容上传(更新/完成)
任务反馈证据内容上传(更新/发送)