## Definition
No. | Roles | Description | Output
1 | BA | Business Analysis | Wireframe, Business flow chart, User Story
2 | DEV | JAVA development | Software, Deployment, Java Doc
3 | Testing | Software testing | Functional Testing (Test Case, Test Report)

## Effort Estimatiion
SOW of Netsync |  |  |  | Efforts |  |  | Effort Total
No. | Modle | Features | Description | BA | DEV | Testing
1 | Task Management |  |  | 3.5 | 7.5 | 1.8333 | 12.8333
1.1 |  | Task List Query |  | 0.5 | 2 | 0.41667 | 2.9167
1.2 |  | Task Detail Information |  | 1 | 2 | 0.5 | 3.5
1.3 |  | Resend Task |  | 0.5 | 1 | 0.25 | 1.75
1.4 |  | Remove Pending Task |  | 0.5 | 0.5 | 0.16667 | 1.1667
1.5 |  | Resend batch Tasks |  | 0.5 | 1 | 0.25 | 1.75
1.6 |  | Remove Pending batch Tasks |  | 0.5 | 1 | 0.25 | 1.75
2 | User Management |  |  | 1.5 | 4 | 0.91667 | 6.4167
2.1 |  | User List Query |  | 0.25 | 1 | 0.20833 | 1.4583
2.2 |  | CUD User |  | 0.25 | 1 | 0.20833 | 1.4583
2.3 |  | Define User Group |  | 0.5 | 1 | 0.25 | 1.75
2.4 |  | Define User Rights |  | 0.5 | 1 | 0.25 | 1.75
3 | Group Management |  |  | 0.75 | 2 | 0.45833 | 3.2083
3.1 |  | Group List Query |  | 0.25 | 0.5 | 0.125 | 0.875
3.2 |  | CUD Groups |  | 0.25 | 1 | 0.20833 | 1.4583
3.3 |  | Define Group Rights |  | 0.25 | 0.5 | 0.125 | 0.875
4 | Access Management |  |  | 1.5 | 3 | 0.75 | 5.25
4.1 |  | Access List Query |  | 0.5 | 1 | 0.25 | 1.75
4.2 |  | CUD Access |  | 1 | 2 | 0.5 | 3.5
5 | Queue Management |  |  | 3 | 6 | 1.5 | 10.5
5.1 |  | Define Queue Logic |  | 1.5 | 3 | 0.75 | 5.25
5.2 |  | Suspend Task in Queue |  | 0.5 | 1 | 0.25 | 1.75
5.3 |  | Prioritize Task in Queue |  | 0.5 | 1.5 | 0.33333 | 2.3333
5.4 |  | Restart Task in Queue |  | 0.5 | 0.5 | 0.16667 | 1.1667
6 | Cache Management (Optional) |  |  | 1.5 | 6 | 1.25 | 8.75
6.1 |  | Define size of Cache |  | 0.5 | 2 | 0.41667 | 2.9167
6.2 |  | Define Business Objects of cache |  | 0.5 | 2 | 0.41667 | 2.9167
6.3 |  | Define page in & page out logic |  | 0.5 | 2 | 0.41667 | 2.9167
7 | Connection Management |  |  | 2.5 | 5 | 1.25 | 8.75
7.1 |  | CUD Connections | Define Destined Backend System Define Destined Frontend System Define Business Objects Define Standard API to Frontend Define Predefined API to Backend Test Connection | 1.5 | 3 | 0.75 | 5.25
7.2 |  | Query Connections |  | 0.5 | 1 | 0.25 | 1.75
7.3 |  | View Connection Details |  | 0.5 | 1 | 0.25 | 1.75
8 | Business Model Management |  |  | 3.5 | 11 | 2.4167 | 16.9167
8.1 |  | CRUD business model |  | 1 | 2 | 0.5 | 3.5
8.2 |  | API for common Business model API (inbound) |  | 0.5 | 2 | 0.41667 | 2.9167
8.3 |  | API for common Business model API (outbound) |  | 0.5 | 2 | 0.41667 | 2.9167
8.4 |  | Test Business Model |  | 0.5 | 1 | 0.25 | 1.75
8.5 |  | Combine Business Model |  | 0.5 | 2 | 0.41667 | 2.9167
8.6 |  | API for combined business model |  | 0.5 | 2 | 0.41667 | 2.9167
9 | Log Management |  |  | 1.5 | 3 | 0.75 | 5.25
9.1 |  | Log List Query |  | 0.5 | 1 | 0.25 | 1.75
9.2 |  | View Log Detail |  | 0.5 | 1 | 0.25 | 1.75
9.3 |  | Tracking Log in Live Mode |  | 0.5 | 1 | 0.25 | 1.75
10 | System Monitoring |  |  | 5 | 12 | 2.8333 | 19.8333
10.1 |  | Queue Status |  | 0.5 | 2 | 0.41667 | 2.9167
10.2 |  | JVM Monitoring |  | 1 | 2 | 0.5 | 3.5
10.3 |  | CPU/Memory Monitoring |  | 0.5 | 2 | 0.41667 | 2.9167
10.4 |  | System alarm (mail/sms) |  | 0.5 | 2 | 0.41667 | 2.9167
10.5 |  | Monitoring report |  | 2 | 2 | 0.66667 | 4.6667
10.6 |  | Connection status to backend system |  | 0.25 | 1 | 0.20833 | 1.4583
10.7 |  | Connection status to frontend system |  | 0.25 | 1 | 0.20833 | 1.4583
11 | Job Management |  |  | 2 | 4 | 1 | 7
11.1 |  | CRUD Jobs | View Jobs Status Define Job type Schedule management Executable Script support | 2 | 4 | 1 | 7
12 | Security Control |  |  | 2 | 5 | 1.1667 | 8.1667
12.1 |  | Oauth Settings |  | 1 | 3 | 0.66667 | 4.6667
12.2 |  | SSL Settings |  | 1 | 2 | 0.5 | 3.5
13 | Archive Management |  |  | 2 | 5.5 | 1.25 | 8.75
13.1 |  | Archive Schedule |  | 0.5 | 1.5 | 0.33333 | 2.3333
13.2 |  | Archive scope (business object level) |  | 0.5 | 1.5 | 0.33333 | 2.3333
13.3 |  | Archive scope (task) |  | 0.5 | 1.5 | 0.33333 | 2.3333
13.4 |  | Archive jobs management (Activate/Deactivate) |  | 0.5 | 1 | 0.25 | 1.75
14 | Report |  |  | 4 | 5 | 1.5 | 10.5
14.1 |  | Task Statistic |  | 1 | 1 | 0.33333 | 2.3333
14.2 |  | Error Statistic |  | 1 | 2 | 0.5 | 3.5
14.3 |  | Queue Health Statistic |  | 1 | 1 | 0.33333 | 2.3333
14.4 |  | Server Health Statistic |  | 1 | 1 | 0.33333 | 2.3333
|  |  | Total | 34.25 | 79 | 18.875 | 132.125